## As-Is Process Map
BKKB Monthly Welfare Grant: As-Is Service Process Map
Built from BKKB_Monthly_Welfare_Grant_AsIs.bpmn. Orange rows are inferred, not steps in the source map. Red rows are the defect exception path. Blue rows recur monthly.
Seq | Step ID | Source reference | Phase | Organisation | Performer | Activity | Input | Output | Next step / hand-off | Channel / medium | Stated time (source) | Min (h) | Max (h) | Min (working days) | Max (working days) | Citizen visits (in person) | Cost to citizen (BDT) | Activity type | Basis | Observations
1 | A1 | Table step 1 (map 1) | P0. Application and attestation | Legal heir / applicant | Applicant | Register on portal, fill in and print online application | Death or disability of employee; decision to claim | Printed application form | E0 (employer attestation) | Online (sss.bkkb.gov.bd) | Not stated | [5 empty] | Not stated | Citizen action | Source | Applicant may be the employee in disability cases, not an heir.
2 | E0 | Document list items 1 to 9 and 11 | P0. Application and attestation | Employer's office | Employer office | Attest document copies, countersign UP certificates, sign and seal application form | Printed form; 11 supporting documents | Attested documents; signed and sealed form | A2 (applicant) | In person; paper | Not stated |  |  |  |  | 1 | Not stated | Verification (attestation) | Inferred | 10 of 11 documents need office attestation or countersignature. At least one in-person visit by the applicant.
3 | A2 | Table step 2 (map 1) | P0. Application and attestation | Legal heir / applicant | Applicant | Upload signed form and scanned documents; final submit | Attested documents; signed form | Online submission | E1 (employer forwards hard copy) | Online | Not stated | [5 empty] | Not stated | Citizen action | Source | No flow from the portal into the BKKB back office is shown. BKKB processing starts from the hard copy (E1).
4 | E1 | Table step 3 (map 2) | P0. Application and attestation | Employer's office | Employer office | Forward hard copy application with documents to BKKB | Attested hard copy file | Hard copy file received at BKKB | S4 (BKKB helpdesk) | By hand or post | Not stated | [5 empty] | Not stated | Despatch | Source | Duplicates the online submission. Postal or courier transit time not stated.
5 | S4 | Table step 4 | A. Intake and downward marking | BKKB Head Office | Helpdesk (information provider) | Receive hard copy application | Hard copy application | Application received | S5 (DG) | Paper | Immediate | 0 | 0 | 0 | 0 |  |  | Receipt and routing | Source
6 | S5 | Table step 5 | A. Intake and downward marking | BKKB Head Office | Director General | Mark application | Received application | Marked application | S6 (PA to DG) | Paper file | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Marking / routing | Source | No decision taken. First of five marking steps before the section opens a file.
7 | S6 | Table step 6 | A. Intake and downward marking | BKKB Head Office | PA to DG | Enter in register; route onward | Marked application | Register entry; application routed | S7 (Director, Admin) | Paper register | 0.5-1 h | 0.5 | 1 | 0.0625 | 0.125 |  |  | Record-keeping | Source | Step label says route to Additional DG, but the next step is Director (Admin). Confirm with BKKB.
8 | S7 | Table step 7 | A. Intake and downward marking | BKKB Head Office | Director (Admin) | Mark application | Routed application | Marked application | S8 (DD, Admin) | Paper file | 3-4 h | 3 | 4 | 0.375 | 0.5 |  |  | Marking / routing | Source
9 | S8 | Table step 8 | A. Intake and downward marking | BKKB Head Office | Deputy Director (Admin) | Mark application | Marked application | Marked application | S9 (AD, Welfare) | Paper file | 3-4 h | 3 | 4 | 0.375 | 0.5 |  |  | Marking / routing | Source
10 | S9 | Table step 9 | A. Intake and downward marking | BKKB Head Office | Assistant Director (Welfare) | Mark application; send to section | Marked application | Application in Welfare section | S10 (UDA) | Paper file | 3-4 h | 3 | 4 | 0.375 | 0.5 |  |  | Marking / routing | Source
11 | S10 | Table step 10 | B. Section processing and document check | BKKB Head Office | Office Assistant / UDA | Check index, open file, enter in file register, put up | Application in section | Case file opened and registered | S11 (UDA) | Paper file and register | 1 day | 8 | 8 | 1 | 1 |  |  | Record-keeping | Source
12 | S11 | Table step 11 | B. Section processing and document check | BKKB Head Office | Office Assistant / UDA | Check documents received with application | Case file | Document check result | G1 (decision) | Paper file | 1 day | 8 | 8 | 1 | 1 |  |  | Verification | Source | The only substantive document check in the BKKB process.
13 | G1 | Source map decision | B. Section processing and document check | BKKB Head Office | Office Assistant / UDA | Decision: documents complete? | Document check result | Yes: S13. No: S12 | S13 or S12 | Paper file | Not stated | [6 empty] | Decision | Source | Completeness check only. No eligibility determination and no rejection path documented.
14 | S12 | Table step 12 | R. Defect return and rework (exception) | BKKB Head Office | Office Assistant / UDA | Send SMS to applicant and letter to employer office listing defects | Incomplete file | SMS to applicant; letter to employer | A3 and E_fix (rework); BKKB case closes | SMS; paper letter | Immediate | 0 | 0 | 0 | 0 |  |  | Exception notification | Source | Resubmission arrives as a new hard copy and re-enters at S4, repeating the marking cascade.
15 | A3 | Map rework loop (to step 2) | R. Defect return and rework (exception) | Legal heir / applicant | Applicant | Correct defects in form or documents; re-upload | Defect SMS | Corrected online submission | A2 (re-submit) | Online | Not stated | [5 empty] | Not stated | Citizen action (rework) | Inferred | No time limit or rework cap.
16 | E_fix | Table step 12; map loop to step 2 | R. Defect return and rework (exception) | Employer's office | Employer office | Inform applicant; obtain corrected documents; re-attest and re-forward | Defect letter | Corrected hard copy file | E1 (re-forward) | In person; paper | Not stated |  |  |  |  | 1 | Not stated | Rework | Source | Runs in parallel with A3. Two rework loops for one defect.
17 | S13 | Table step 13 | C. Upward approval chain | BKKB Head Office | AD (Welfare) / Welfare Officer | Approve; put up to Deputy Director | Complete case file | Approval note; file put up | S14 (DD) | Paper file | Not stated | [6 empty] | Approval | Source | Time not stated in source.
18 | S14 | Table step 14 | C. Upward approval chain | BKKB Head Office | Deputy Director (Admin) | Check and approve | File with approval note | Approval | S15 (Director) | Paper file | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Approval | Source | No return or rejection outcome documented.
19 | S15 | Table step 15 | C. Upward approval chain | BKKB Head Office | Director (Admin) | Check file and draft order | File | Draft order approved | S16 (ADG) | Paper file | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Approval | Source
20 | S16 | Table step 16 | C. Upward approval chain | BKKB Head Office | Additional DG | Approve; put up to DG | File and draft order | Approval | S17 (DG) | Paper file | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Approval | Source | Source map omits this step. Confirm with BKKB.
21 | S17 | Table step 17 | C. Upward approval chain | BKKB Head Office | Director General | Final approval; file goes down | File and draft order | Approved order | S18 (Director) | Paper file | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Approval | Source | Table names DG as final approver; map shows ADG. Confirm with BKKB.
22 | S18 | Table step 18 | D. File returned down | BKKB Head Office | Director (Admin) | Send file down | Approved file | File routed down | S19 (DD) | Paper file | 0.5-1 h | 0.5 | 1 | 0.0625 | 0.125 |  |  | Marking / routing | Source
23 | S19 | Table step 19 | D. File returned down | BKKB Head Office | Deputy Director (Admin) | Send file down | Approved file | File routed down | S20 (AD) | Paper file | 0.5-1 h | 0.5 | 1 | 0.0625 | 0.125 |  |  | Marking / routing | Source
24 | S20 | Table step 20 | D. File returned down | BKKB Head Office | Assistant Director (Welfare) | Receive file in section | Approved file | File in section | S21 (Welfare Officer) | Paper file | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Marking / routing | Source
25 | S21 | Table step 21 | E. Card printing and registration | BKKB Head Office | Welfare Officer | Print approved order as three colour cards; send to UDA | Approved order | Three cards (applicant, bank and office copies) | S22 (UDA) | Paper cards | 1 day | 8 | 8 | 1 | 1 |  |  | Document production | Source | Paper card is the payment instrument.
26 | S22 | Table step 22 | E. Card printing and registration | BKKB Head Office | Office Assistant / UDA | Enter card numbers in register; send to Accounts Officer | Printed cards | Card register entry | S23 (Accounts Officer) | Paper register | 4-5 h | 4 | 5 | 0.5 | 0.625 |  |  | Record-keeping | Source
27 | S23 | Table step 23 | E. Card printing and registration | BKKB Head Office | Accounts Officer (Welfare) | Sign card register | Card register | Signed register | S24 (UDA) | Paper register | 0.5-1 h | 0.5 | 1 | 0.0625 | 0.125 |  |  | Signature | Source
28 | S24 | Table step 24 | F. Card despatch to beneficiary | BKKB Head Office | Office Assistant / UDA | Prepare forwarding letter for applicant card | Applicant copy of card | Draft forwarding letter | S25 (AD) | Paper letter | 1 day | 8 | 8 | 1 | 1 |  |  | Document production | Source | Card path (S24 to S27) runs before the bank path (S28 to S33) although the two are independent.
29 | S25 | Table step 25 | F. Card despatch to beneficiary | BKKB Head Office | Assistant Director (Welfare) | Sign forwarding letter | Draft letter | Signed letter | S26 (Despatch Rider) | Paper letter | 4-5 h | 4 | 5 | 0.5 | 0.625 |  |  | Signature | Source
30 | S26 | Table step 26 | F. Card despatch to beneficiary | BKKB Head Office | Despatch Rider | Post applicant card to employer office by registered mail | Card and signed letter | Card in registered post | S27 (Office Assistant); E_hand (employer) | Registered post | 1 day | 8 | 8 | 1 | 1 |  |  | Despatch | Source | Postal transit time to employer not stated.
31 | S27 | Table step 27 | F. Card despatch to beneficiary | BKKB Head Office | Office Assistant / UDA | File registry slip in case file | Registry slip | Updated case file | S28 (UDA) | Paper file | 0.5-1 h | 0.5 | 1 | 0.0625 | 0.125 |  |  | Record-keeping | Source
32 | E_hand | Comparison table, section 3(2) | F. Card despatch to beneficiary | Employer's office | Employer office | Hand over card to beneficiary, collected in person | Card received by post | Card with beneficiary | A_pay (applicant) | In person | Not stated |  |  |  |  | 1 | Not stated | Hand-over | Source | Additional in-person visit by the beneficiary. Card may arrive before the branch holds its copy.
33 | S28 | Table step 28 | G. Bank instruction | BKKB Head Office | Office Assistant / UDA | Prepare card list and letter to Sonali Bank, Ramna | Bank copies of cards | Draft list and letter | S29 (AD) | Paper list and letter | 1 day | 8 | 8 | 1 | 1 |  |  | Document production | Source | Starts only after the card path completes.
34 | S29 | Table step 29 | G. Bank instruction | BKKB Head Office | Assistant Director (Welfare) | Sign file | Draft list and letter | Signed file | S30 (DD) | Paper file | 5-6 h | 5 | 6 | 0.625 | 0.75 |  |  | Signature | Source
35 | S30 | Table step 30 | G. Bank instruction | BKKB Head Office | Deputy Director (Admin) | Sign list and letter | Signed file | Signed list and letter | S31 (AD) | Paper | 2-3 h | 2 | 3 | 0.25 | 0.375 |  |  | Signature | Source
36 | S31 | Table step 31 | G. Bank instruction | BKKB Head Office | Assistant Director (Welfare) | Sign file; file goes down | Signed list and letter | File signed again | S32 (Office Assistant) | Paper file | 0.5-1 h | 0.5 | 1 | 0.0625 | 0.125 |  |  | Signature | Source | AD signs twice, either side of the DD signature at S30.
37 | S32 | Table step 32 | G. Bank instruction | BKKB Head Office | Office Assistant / UDA | Issue letter | Signed list and letter | Issued letter | S33 (Despatch Rider) | Paper letter | 3-4 h | 3 | 4 | 0.375 | 0.5 |  |  | Document production | Source
38 | S33 | Table step 33 | G. Bank instruction | BKKB Head Office | Despatch Rider | Send list, letter and bank-copy cards to Ramna by peon | Issued letter, list and cards | Package delivered to Ramna | S34 (Ramna) | Hand delivery by peon | 1 day | 8 | 8 | 1 | 1 |  |  | Despatch | Source | BKKB case closes here.
39 | S34 | Table step 34 | H. Bank distribution | Sonali Bank, Ramna Corporate Branch | Ramna Corporate Branch | Send bank-copy cards to paying branches | List, letter and bank-copy cards | Cards at paying branches | Br1 (paying branch) | Internal bank despatch | 7 days | 56 | 56 | 7 | 7 |  |  | Despatch | Source | Largest single stated step. Ramna acts as a physical relay only.
40 | Br1 | Source section 2(a) | H. Bank distribution | Sonali Bank, paying branch | Paying branch | File bank-copy card against case | Bank-copy card | Card on file at branch | Br2 (on beneficiary visit) | Paper file | Not stated | [6 empty] | Record-keeping | Inferred | Not mapped in source.
41 | A_pay | Terms of service 1 and 2; challenge 1 | I. Monthly disbursement (recurring) | Legal heir / applicant | Beneficiary | Present card and certificate at branch; withdraw cash | Applicant card; certificate | Cash received | Br2 (branch) | In person at branch | Not stated |  |  |  |  | 1 | Not stated | Citizen action (payment) | Inferred | Repeats monthly for up to 15 years, i.e. up to 180 branch visits.
42 | Br2 | Terms of service 1 and 2 | I. Monthly disbursement (recurring) | Sonali Bank, paying branch | Paying branch | Check card, certificate and signature; pay cash | Card; certificate; bank-copy card | Cash paid; card endorsed | End (monthly cycle) | Over the counter, cash | Not stated | [6 empty] | Payment | Inferred | Repeats every month.

## Summary
Summary of stated times, effort and structure
All figures calculate from the 'As-Is Process Map' sheet. Working day = hours set on the Assumptions sheet.
1. Stated time by phase
Phase | Steps | Steps with no stated time | Min (h) | Max (h) | Min (working days) | Max (working days)
P0. Application and attestation | 4 | 4 | 0 | 0 | 0 | 0
A. Intake and downward marking | 6 | 0 | 11.5 | 16 | 1.4375 | 2
B. Section processing and document check | 3 | 1 | 16 | 16 | 2 | 2
R. Defect return and rework (exception) | 3 | 2 | 0 | 0 | 0 | 0
C. Upward approval chain | 5 | 1 | 8 | 12 | 1 | 1.5
D. File returned down | 3 | 0 | 3 | 5 | 0.375 | 0.625
E. Card printing and registration | 3 | 0 | 12.5 | 14 | 1.5625 | 1.75
F. Card despatch to beneficiary | 5 | 1 | 20.5 | 22 | 2.5625 | 2.75
G. Bank instruction | 6 | 0 | 26.5 | 30 | 3.3125 | 3.75
H. Bank distribution | 2 | 1 | 56 | 56 | 7 | 7
I. Monthly disbursement (recurring) | 2 | 2 | 0 | 0 | 0 | 0
BKKB pre-decision (A to C) | 14 | 2 | 35.5 | 44 | 4.4375 | 5.5
BKKB post-decision (D to G) | 17 | 1 | 62.5 | 71 | 7.8125 | 8.875
BKKB total (A to G) | 31 | 3 | 98 | 115 | 12.25 | 14.375
Stated total, BKKB receipt to cards at branches (A to H) | 33 | 4 | 154 | 171 | 19.25 | 21.375 | Excludes P0, rework (R), monthly disbursement (I), postal transit and S13.
Post-decision share of BKKB time (min / max) |  |  | 63.78% | 61.74%
Critical-path saving if card path (F) runs in parallel with bank path (G) |  |  | 20.5 | 22 | 2.5625 | 2.75 | Valid because G is longer than F, so F leaves the critical path.
2. Workload by performer
Performer | Organisation | Steps | Min (h) | Max (h) | Min (working days) | Max (working days)
Applicant | Legal heir / applicant | 3 | 0 | 0 | 0 | 0
Employer office | Employer's office | 4 | 0 | 0 | 0 | 0
Helpdesk (information provider) | BKKB Head Office | 1 | 0 | 0 | 0 | 0
Director General | BKKB Head Office | 2 | 4 | 6 | 0.5 | 0.75
PA to DG | BKKB Head Office | 1 | 0.5 | 1 | 0.0625 | 0.125
Director (Admin) | BKKB Head Office | 3 | 5.5 | 8 | 0.6875 | 1
Deputy Director (Admin) | BKKB Head Office | 4 | 7.5 | 11 | 0.9375 | 1.375
Assistant Director (Welfare) | BKKB Head Office | 5 | 14.5 | 19 | 1.8125 | 2.375
Office Assistant / UDA | BKKB Head Office | 9 | 39.5 | 42 | 4.9375 | 5.25
AD (Welfare) / Welfare Officer | BKKB Head Office | 1 | 0 | 0 | 0 | 0
Additional DG | BKKB Head Office | 1 | 2 | 3 | 0.25 | 0.375
Welfare Officer | BKKB Head Office | 1 | 8 | 8 | 1 | 1
Accounts Officer (Welfare) | BKKB Head Office | 1 | 0.5 | 1 | 0.0625 | 0.125
Despatch Rider | BKKB Head Office | 2 | 16 | 16 | 2 | 2
Ramna Corporate Branch | Sonali Bank, Ramna Corporate Branch | 1 | 56 | 56 | 7 | 7
Paying branch | Sonali Bank, paying branch | 2 | 0 | 0 | 0 | 0
Beneficiary | Legal heir / applicant | 1 | 0 | 0 | 0 | 0
3. Steps by activity type
Activity type | All steps | BKKB steps | Min (h) | Max (h)
Citizen action | 2 | 0 | 0 | 0
Verification (attestation) | 1 | 0 | 0 | 0
Despatch | 4 | 2 | 72 | 72
Receipt and routing | 1 | 1 | 0 | 0
Marking / routing | 7 | 7 | 14 | 20
Record-keeping | 5 | 4 | 13 | 15
Verification | 1 | 1 | 8 | 8
Decision | 1 | 1 | 0 | 0
Exception notification | 1 | 1 | 0 | 0
Citizen action (rework) | 1 | 0 | 0 | 0
Rework | 1 | 0 | 0 | 0
Approval | 5 | 5 | 8 | 12
Document production | 4 | 4 | 27 | 28
Signature | 5 | 5 | 12 | 16
Hand-over | 1 | 0 | 0 | 0
Citizen action (payment) | 1 | 0 | 0 | 0
Payment | 1 | 0 | 0 | 0
Total | 42 | 31
4. TCVQ baseline, citizen perspective (input to SPS Chhok 7)
Dimension | As-Is value | Basis / note
Time: stated, BKKB receipt to cards at branches (working days, min) | 19.25 | From section 1. Excludes P0, rework, postal transit and S13.
Time: stated, BKKB receipt to cards at branches (working days, max) | 21.375 | As above. True citizen time is longer and not measured.
Visits: onboarding, no rework (employer attestation + card collection) | 2 | Minimum. Attestation may need separate drop-off and collection visits.
Visits: added per rework cycle | 1 | Employer re-attestation.
Visits: monthly disbursement, per month | 1 | Branch visit to withdraw cash.
Visits: monthly disbursement, over grant life (max) | 180 | Up to 15 years.
Cost to citizen (BDT) | Not stated | Travel, copying and attestation costs not in source. Collect in citizen survey.
Documents submitted / needing attestation | 11 / 10 | Source document list.
Quality: defect notification | SMS + letter | No rejection path, no time limit, no status tracking documented.
5. Structural counts (BKKB, main path)
Measure | Value | Basis
BKKB steps (S4 to S33, incl. decision G1) | 31 | Formula
Internal hand-offs between roles, S4 to S33 main path | 25 | Counted from lane sequence
Sign-offs per case (5 approvals + 5 post-approval signatures) | 10 | Formula
Marking / routing steps with no decision | 7 | Formula
Manual registers or slips (S6, S10, S22, S27) | 4 | Counted
Supporting documents / documents needing attestation | 11 / 10 | Source document list
Maximum monthly branch visits over grant life (12 x 15 years) | 180 | Terms of service

## Issues & Gaps
Open issues, model inconsistencies and measurement gaps
ID | Ref | Category | Issue | Implication | Confirm with
I01 | S6 | Model inconsistency | S6 label says route to Additional DG, but the next step is S7 Director (Admin). The ADG lane holds only S16. | Either the label or the routing is wrong; affects marking-chain length. | BKKB Admin
I02 | S16 / S17 | Model inconsistency | Step table names DG as final approver (S17); source map shows ADG (map step 15) and omits S16. | Approval chain may be four or five levels. | BKKB Admin
I03 | S13 to S17 | Structural gap | All five approvals are modelled as approve only. No return or rejection outcome documented. | Either approvals add no independent check, or an undocumented exception path exists. | BKKB Welfare section
I04 | G1 | Structural gap | Only a completeness check exists. No eligibility determination or ineligibility path is documented. | Eligibility appears to be assumed from employer attestation. | BKKB Welfare section
I05 | S12 / S4 | Assumption | Model assumes a corrected file re-enters at S4 and repeats the full marking cascade. | Rework cost per cycle of at least 3.4 to 4 working days inside BKKB if confirmed. | BKKB Welfare section
I06 | A2 / E1 | Structural finding | The online submission has no downstream consumer at BKKB; processing starts from the hard copy. | Citizen submits twice, once online and once on paper through the employer. | BKKB IT; Welfare section
I07 | A_pay / Br2 | Model inconsistency | Monthly cash withdrawal is modelled as a single occurrence. | Understates the largest citizen burden (up to 180 visits). Add loop marker or recurring sub-process. | Model owner
I08 | E_hand / Br1 | Structural gap | Beneficiary may receive the card before Ramna's 7-day distribution reaches the branch. | Risk of a failed first branch visit; not shown in model. | Sonali Bank
I09 | P0, S13, E_hand, Br1 | Measurement gap | No stated time for applicant and employer steps, S13, card hand-over or branch filing. | True citizen-experienced duration cannot be quantified. | BKKB; employer offices
I10 | All | Measurement gap | No end-to-end time (first action to first cash), rework rate or case volume in source. | No baseline for To-Be targets. | BKKB MIS / file registers
I11 | All T values | Measurement gap | Unclear whether stated times are touch time or elapsed time including queues. '1 day' entries suggest queue time. | Totals may overstate effort and understate elapsed time. | BKKB
I12 | Participant | Model note | Start event refers to the heir; in disability cases the applicant may be the employee. | Wording of trigger and applicant role. | Model owner

## Assumptions & Legend
Assumptions and legend
Working hours per day | 8 | Assumption. Used to convert stated 'day' times to hours and hours to working days. Edit to test sensitivity.
Citizen visit counts are minimums inferred from the model (blue). Cost to citizen is not stated in the source.
Legend
Blue text |  | Hard-coded input from the source (stated times) or a counted value.
Black text |  | Formula.
Yellow fill |  | Assumption you can edit.
Orange row (process map) |  | Inferred step: not in the source map; derived from the service profile, document list or terms of service.
Red row (process map) |  | Defect return and rework exception path.
Blue row (process map) |  | Recurring monthly disbursement (up to 15 years).
'Immediate' |  | Recorded as 0 hours.
'Not stated' |  | Left blank; excluded from totals. Totals therefore understate elapsed time.
Phase P0, R, I |  | Excluded from the stated-time total: P0 and I have no stated times; R is an exception path.
Source |  | BKKB_Monthly_Welfare_Grant_AsIs.bpmn, which references the BKKB step table, source process map, service profile and comparison table.